## Sheet1
System Name | Product Inventory for Small Businesses
Members: | Karen Lean Kay Cabarrubias
Joel M. Verano
Raven King O. Pavo
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September |  |  |  | October |  |  |  | November |  |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4
1. LOGIN
1.1. Creating UI | Raven King O. Pavo | 2024-09-27 | 2024-10-05 | Done
1.2. Integrate with DB | Raven King O. Pavo | 2024-10-06 | 2024-10-12 | Done
2. REGISTER
2.1. Creating UI | Raven King O. Pavo | 2024-09-27 | 2024-10-05 | Done
2.2. Integrate with DB | Raven King O. Pavo | 2024-10-06 | 2024-12-03 | Done
3. USER PROFILE/ROLE MANAGEMENT
3.1. Creating UI for User Profile | Karen Lean Kay Cabarrubias | 2024-11-24 | 2024-11-24 | Done
3.2 Implement User Details Update | Raven King O. Pavo | 2024-11-24 | 2024-11-27 | In-Progress
3.3. Implementing Role-Based Access Control | Raven King O. Pavo | 2024-10-14 | 2024-12-03 | Done
3.4. Integrate with DB for User Management | Raven King O. Pavo | 2024-10-14 | 2024-12-03 | Done
4. DASHBOARD
4.1. Design Dashboard UI | Karen Lean Kay Cabarrubias | 2024-09-25 | 2024-10-03 | Done
4.2. Implement Data Visualization | Karen Lean Kay Cabarrubias | 2024-10-03 | 2024-10-11 | Done
4.3. Integrate Real-Time Data Feeds | Karen Lean Kay Cabarrubias | 2024-10-04 | 2024-11-14 | Done
5. NOTIFICATIONS
5.1. UI for Notifications | Karen Lean Kay Cabarrubias | 2024-09-29 | 2024-10-11 | Done
5.2. Implement Notification Triggers | Karen Lean Kay Cabarrubias | 2024-10-09 | 2024-10-19 | Done
5.3 Implement Stock Threshold Notification | Karen Lean Kay Cabarrubias | 2024-10-09 | 2024-10-19 | Done
5.4 Integrate with DB for Notification Management | Karen Lean Kay Cabarrubias | 2024-10-09 | 2024-10-19 | Done
6. INVENTORY MANAGEMENT
6.1. Adding Products UI | Karen Lean Kay Cabarrubias | 2024-10-24 | 2024-10-26 | Done
6.2. Editing Items UI | Joel M. Verano Jr. | 2024-11-02 | 2024-11-02 | Done
6.3.Implement Categorial Filter Function | Joel M. Verano Jr. | 2024-11-03 | 2024-11-07 | Done
6.4.Implement Search Filter Function | Joel M. Verano Jr. | 2024-11-01 | 2024-11-01 | Done
6.5. Removing Items UI | Joel M. Verano Jr. | 2024-11-02 | 2024-11-02 | Done
6.6. Integrate with DB for Inventory Management | Karen Lean Cabarrubias / Joel M. Verano Jr. | 2024-10-30 | 2024-11-01 | Done
7. SALES MANAGEMENT
7.1. Sales page UI | Joel M. Verano Jr. | 2024-11-23 | 2024-11-27 | Done
7.2.Implement Product Selection | Joel M. Verano Jr. | 2024-12-03 | 2024-12-04 | Done
7.3.Implement Utility Buttons | Joel M. Verano Jr. | 2024-12-03 | 2024-12-04 | Done
7.2. Implement Categorial Filter Function | Joel M. Verano Jr. | 2024-11-23 | 2024-11-27 | Done
7.3. Integrate with DB for Product Management | Joel M. Verano Jr. | 2024-12-03 | 2024-12-04 | Done
8. HISTORY
8.1. UI for History | Karen Lean Kay Cabarrubias | 2024-10-10 | 2024-11-03 | Done
8.2.Implement Sales History | Joel M. Verano Jr. | 2024-11-30 | 2024-12-02 | Done
8.3. Implement Product History | Karen Lean Kay Cabarrubias | 2024-10-20 | 2024-11-04 | Done
8.4. Integrate with DB for Transaction Logs | Joel M. Verano Jr. | 2024-11-30 | 2024-12-02 | Done
10. Base UI Template
10.1.Base UI Template | Joel M. Verano Jr. | 2024-10-18 | 2024-10-27 | Done
11. Additional Features
11.1 Export Data to Excel | Karen Lean Kay Cabarrubias | 2024-11-16 | 2024-11-18 | Done
11.2 Upload Product Image | Karen Lean Kay Cabarrubias | 2024-11-24 | 2024-11-25 | Done